INTRASTACK SOLUTIONS

Odoo CRM Platform

Project Execution Plan & Task Assignment

Version 1.0  |  Draft — Pending Review

Prepared by: Steve (Gia Khiem Do)  |  Tech Lead

Target Go-Live: ~3 months from kickoff

| Item | Detail |
| --- | --- |
| Platform | Odoo 17 Community Edition |
| Domain | crm.intrastack.com |
| Server IP | 163.245.212.92 |
| Deployment | Docker (odoo:17 + postgres:15) |
| Tech Lead | Steve / Khiem (@khiemdztv) |
| Co-Lead | Arian (Asia timezone coverage) |
| Developer | Rishit |
| Project Manager | Auspicious Munemo |
| BA / PM Guide | Luan Nguyen |
| Deadline | 3 months from project start |

# 1. Pre-Kickoff Setup — Completed

The following infrastructure tasks have been completed before the official kickoff. These items are confirmed done and require no further action.

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 1 | Nginx configured for crm.intrastack.com | Steve | Done |
| 2 | DNS A record created: crm.intrastack.com → 163.245.212.92 | Steve | Done |
| 3 | All core Odoo modules activated | Steve | Done |
| 4 | All team members invited and access granted | Steve | Done |
| 5 | SSL certificate (HTTPS) via Certbot | Steve | Done |

# 2. Project Structure & Team Roles

This project follows the IntraStack CRM Platform document (v1.0) across 3 phases. The team of 3 engineers plus PM/BA support targets full Phase 1 completion and Phase 2 initiation within the 3-month window.

| Member | Role | Primary Responsibilities | Availability |
| --- | --- | --- | --- |
| Steve (Khiem) | Tech Lead | 4 CRM pipelines, automation rules, Sales quote engine, CEO dashboard, overall config ownership | Full-time on project |
| Arian | Co-Lead / Dev | Contacts + tagging strategy, Project & Delivery module, Asia timezone async coverage | Full-time on project |
| Rishit | Developer | Custom fields configuration, Timesheets + Employee module, technical support tasks | Full-time on project |
| Auspicious Munemo | Project Manager | Sprint tracking, meeting coordination, progress reporting to Stefan & Luan | Part-time oversight |
| Luan Nguyen | BA / PM (Backend) | Requirements review, acceptance criteria, final sign-off on deliverables | On-demand review |
| Stefan Nguyen | Sponsor / Owner | Final approval, resource decisions, escalation point | Weekly review |

# 3. Phase 1 — Foundation (Month 1 to Month 3)

Phase 1 covers all no-code Odoo configuration as defined in the IntraStack CRM Platform document, Slide 13. This phase must be fully complete before Phase 2 begins.

## 3.1 CRM Pipeline Design (Slide 04)

Create 4 independent Sales Team pipelines in Odoo CRM. Each pipeline is a separate Sales Team with its own Kanban stages. This is the foundation of the entire platform.

| Pipeline | Sales Team Name | Stages | Description | Owner | Week |
| --- | --- | --- | --- | --- | --- |
| P1 | Staffing | 8 | New Requirement → Sourcing → Submitted → Interviews → Offer → Closed Won → Active Billing → Renewal | Steve | 1 |
| P2 | Consulting | 7 | Discovery → Qualification → Solution Design → Proposal → Negotiation → Closed Won → Delivery | Steve | 1 |
| P3 | Subcontracting | 5 | Outreach → Vendor Qualification → Capability Review → Approved Vendor → Active Engagement | Steve | 1 |
| P4 | Managed Services | 6 | Qualified Lead → Assessment → Proposal → Contract → Active Service → Renewal | Steve | 1 |

### Steps to create each pipeline:

- Go to CRM → Configuration → Sales Teams → Create new team

- Set team name (e.g. "P1 — Staffing"), assign team leader (Steve)

- Go to CRM → Configuration → Stages → Create stages specific to that pipeline

- Assign stages to the correct Sales Team only (uncheck other teams)

- Test by creating a sample opportunity in each pipeline and moving it across stages

## 3.2 Custom Fields & CRM Configuration (Slide 05)

Add the following custom fields to every CRM opportunity record. These are mandatory on every deal.

| Field Name | Field Type | Options / Values | Mandatory? | Owner | Week |
| --- | --- | --- | --- | --- | --- |
| Deal Classification | Selection | Staffing / Consulting / Subcontracting / Managed Services | Yes | Rishit | 1 |
| Service Category | Selection | Cloud / AI/ML / Cybersecurity / DevOps / Data Engineering / App Modernization | Yes | Rishit | 1 |
| Urgency Flag | Selection | Immediate (0-30 days) / Short-term (30-90 days) / Long-term (90+ days) | Yes | Rishit | 1 |
| Source Tracking | Selection | LinkedIn / MSP Outreach / Prime Contractor / Referral / Vendor Portal | Yes | Rishit | 1 |
| Expected Value ($) | Monetary | Free numeric input in USD | Yes | Rishit | 1 |
| Decision Maker Flag | Boolean (Yes/No) | Checkbox: Is contact the decision maker? | Yes | Rishit | 1 |

### Steps to add custom fields:

- Enable developer mode: Settings → Activate Developer Mode

- Go to CRM → any opportunity → click gear icon → Add Custom Field

- Set field type, label, and options for each field above

- Mark fields as Required to enforce mandatory entry

- Verify fields appear on all 4 pipeline opportunity forms

## 3.3 Contacts & Tagging Strategy (Slide 09)

Configure the Contacts module to serve as the unified relationship database for all entity types. Every person or company in the system must be tagged accordingly.

| Contact Type | Description | Required Tags |
| --- | --- | --- |
| Client | Direct buyers of staffing, consulting & managed services | Staffing Buyer / Cybersecurity Client (as applicable) |
| MSP Partner | Managed Service Providers — subcontracting channel | MSP Partner, Subcontracting Lead |
| Prime Contractor | Federal & enterprise primes for subcontracting deals | Prime Contractor |
| Candidate | Active & bench engineers — 30+ talent pool | Candidate, technology tags (AWS / Azure etc.) |
| Vendor | Technology & tools vendors used in delivery | Vendor |
| Recruiter Partner | External recruiters for sourcing & placements | Recruiter Partner |

### Tags to create in Contacts → Configuration → Tags:

- AWS Partner

- Azure Partner

- Cybersecurity Client

- Staffing Buyer

- Subcontracting Lead

- MSP Partner

- Prime Contractor

- Candidate

- Vendor

- Recruiter Partner

Owner: Arian  |  Target: Week 1

## 3.4 Automation Logic — Activities System (Slide 06)

Odoo Community Edition has no advanced workflow automation. We use the Activities system as a replacement. The following 4 rules (R1-R4) must be configured as Automated Actions.

| Rule | Trigger | Action | Assigned To | Owner | Week |
| --- | --- | --- | --- | --- | --- |
| R1 | New Lead / Opportunity Created | Create Activity: "Qualify Lead within 24 hours" | Sales Lead (Steve) | Steve | 2 |
| R2 | Stage changed to: New Requirement (P1) | Create Activity: "Submit 5 candidates in 48 hours" | Recruiter (Rishit) | Steve | 2 |
| R3 | Stage changed to: Discovery (P2) | Create Activity: "Prepare discovery checklist + schedule call" | Account Exec (Arian) | Steve | 2 |
| R4 | No activity logged for 5+ days | Manual Task Alert: "Re-engage prospect" | Pipeline Manager | Steve | 2 |

### Steps to configure automation rules:

- Go to Settings → Technical → Automated Actions (developer mode required)

- Create new Automated Action: Model = CRM Lead/Opportunity

- Set Trigger: Stage is set to / Record created / Based on a timed condition

- Action type: Create Activity — set summary, deadline offset, and assigned user

- Test each rule by creating a test opportunity and verifying the activity is triggered

## 3.5 Project & Delivery Module (Slide 07)

Configure the Project module to receive deals from CRM. When a deal is marked Closed Won, a structured project must be created (manually in Community Edition).

| Engagement Type | Project Template Tasks | Owner | Week |
| --- | --- | --- | --- |
| Staffing Engagement | Requirement intake → Sourcing → Screening → Placement → Onboarding | Arian | 2 |
| Consulting Engagement | Architecture Design → Infrastructure Setup → Migration Execution → Validation & Testing → Handover & Docs | Arian | 2 |
| Managed Service | Service Design → Onboarding → SLA Configuration → Go-Live → Renewal Planning | Arian | 2 |

### Key engineering rules (must be enforced):

- Every CRM Closed Won deal triggers manual project creation — never skip this step

- Assign a project manager at deal close

- Link timesheets to the project from Day 1 — retroactive fixes are expensive

- Use task dependencies where applicable

- Enable client portal access per project if requested

## 3.6 Timesheets & Utilization Control (Slide 08)

Configure the Timesheets module to track all engineer hours. Target utilization rate: 70-85% for all consultants. Timesheets must be linked to both Project AND Employee from day one.

| Configuration Item | Details | Owner | Week |
| --- | --- | --- | --- |
| Enable timesheets on projects | Project → Settings → Enable Timesheets | Rishit | 2 |
| Link Employees to projects | Every active project must have employees assigned before work begins | Rishit | 2 |
| Set hourly cost per employee | Employees → employee record → HR Settings → Hourly Cost | Rishit | 2 |
| Configure timesheet approval | Timesheets → Configuration → set approval workflow | Rishit | 3 |
| Create utilization report view | Group timesheets by Employee, filter by Project for burn rate view | Steve | 3 |

## 3.7 Sales & Quote Engine (Slide 10)

Configure 3 Sales quotation templates in Odoo Sales. All quotes, contracts, and rate cards must be generated inside Odoo — never in external documents.

| Document Type | Required Fields | Owner | Week |
| --- | --- | --- | --- |
| Staffing Rate Card | Resource name & role, Bill rate, Pay/cost rate, Duration, Gross margin % | Steve | 3 |
| Consulting SOW | Scope description, Deliverables list, Milestones & timelines, Fixed fee or T&M rate, Acceptance criteria | Steve | 3 |
| Managed Services Contract | Service scope & SLAs, Monthly recurring fee, Resource allocation, Renewal terms, Escalation procedures | Steve | 3 |

### Steps to create quote templates:

- Go to Sales → Configuration → Quotation Templates → Create new

- Add product lines for each service type (use service products, not stockable)

- Add optional sections and notes per document type requirements above

- Assign template to the correct CRM pipeline for auto-selection

## 3.8 CEO Dashboard — Saved Views (Slide 11)

Build the CEO dashboard as Odoo "Favorite" saved views. No Enterprise license required. The following KPI views must be configured and pinned for management.

| Dashboard View | Module | Configuration | Owner | Week |
| --- | --- | --- | --- | --- |
| Total Pipeline Value | CRM | Sum of Expected Revenue across all 4 pipelines, group by stage | Steve | 3 |
| Open Proposals | CRM | Filter: Stage = Proposal (P2 + P4), count | Steve | 3 |
| Active Placements | CRM | Filter: Stage = Active Billing (P1), count | Steve | 3 |
| Revenue Forecast | CRM | Filter: Probability > 50%, sum Expected Revenue, current month | Steve | 3 |
| Pipeline by Deal Type | CRM | Group by Deal Classification field, show % breakdown | Steve | 3 |
| Subcontracting Pipeline Status | CRM | Filter: P3 pipeline, group by stage | Steve | 3 |
| Stalled Deals (>7 days) | CRM | Filter: Last activity date > 7 days ago, no activity | Steve | 3 |

## 3.9 Team Training Session (Slide 13)

A mandatory training session must be conducted for all IntraStack team members who will use the platform before go-live. Steve will facilitate.

| Training Topic | Duration | Target Audience |
| --- | --- | --- |
| Platform overview: 4 pipelines & how to navigate | 20 min | All users |
| Creating & managing opportunities (with custom fields) | 20 min | Sales / Account Execs |
| Daily operating playbook: Morning / Midday / EOD routine | 15 min | All users |
| Logging timesheets correctly (Project + Employee linking) | 15 min | Engineers / Consultants |
| Generating quotes & SOWs from Sales module | 15 min | Sales / Account Execs |
| Critical rules walkthrough (R1-R4, 4 mandatory fields) | 10 min | All users |
| Q&A and practice session | 25 min | All users |

Training Owner: Steve  |  Target: Week 4  |  Format: Live session + recorded walkthrough

# 4. Master Timeline & Sprint Plan

The 2-month remaining timeline is divided into 4 weekly sprints. All Phase 1 deliverables must be complete by end of Week 4. Phase 2 work begins in Month 2.

| Week | Sprint Focus | Steve (Lead) | Arian (Co-Lead) | Rishit (Dev) | PM Check |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Foundation Config | 4 CRM Pipelines + stage definitions | Contacts module + all tags | All 6 custom fields | Kickoff meeting, confirm access |
| Week 2 | Automation + Delivery | Automation rules R1-R4, test all triggers | Project templates (3 types), task structures | Timesheets setup, Employee linking | Mid-sprint check-in |
| Week 3 | Sales + Dashboard | Sales quote engine (3 templates), CEO dashboard 7 saved views | Project portal access config, UAT support | Timesheet approval workflow, cost config | Review dashboard with Luan |
| Week 4 | Training + UAT | Facilitate team training, fix bugs from UAT | UAT testing all 4 pipelines end-to-end | UAT testing timesheets + invoicing flow | Sign-off meeting with Stefan & Luan |
| Month 2 Week 1 | Phase 2 Prep | Scope email automation requirements | Research ATS integration options | Invoice automation setup | Phase 2 planning session |
| Month 2 Week 2-4 | Phase 2 Build | AI lead scoring module research + config | Subcontractor portal planning | Automated email sequences | Weekly progress reports to Stefan |

# 5. Critical Operating Rules (Non-Negotiable)

The following 4 rules from the IntraStack CRM Platform document (Slide 12) are non-negotiable and must be enforced from Day 1 of go-live. Steve is responsible for training all users on these rules.

| # | Rule | Detail | Consequence of Violation |
| --- | --- | --- | --- |
| 01 | Everything Enters CRM First | No leads, conversations, or referrals may be tracked outside Odoo. Zero exceptions — no Excel, no Notion, no sticky notes. | Immediate escalation to Pipeline Manager |
| 02 | No Deal Exists Outside Odoo | Email thread or spreadsheet tracking = system failure. Must be escalated immediately to Steve. | Deal data treated as unofficial until entered |
| 03 | Every Opportunity Must Have 4 Fields | Owner assigned + Expected value entered + Stage set + Next action logged. Incomplete records block pipeline reporting. | Record flagged as incomplete, owner notified |
| 04 | No Inactive Deals > 7 Days | If no activity logged for 7 days, pipeline manager is automatically notified via Activity (R4 automation rule). | Auto-alert fired, deal reviewed in next standup |

# 6. Phase 2 Overview — Automation (Month 2-3)

Phase 2 begins after Phase 1 sign-off. These items require development effort beyond UI configuration. Scope and timeline for each item should be confirmed with Stefan and Luan at the end of Month 1.

| Feature | Description | Effort Estimate | Owner | Priority |
| --- | --- | --- | --- | --- |
| Automated Email Sequences | Follow-up email chains triggered by CRM stage changes | Medium — Odoo mail template config | Steve | High |
| AI Lead Scoring Module | Score leads based on source, deal size, and engagement | High — requires custom Python module or OCA add-on | Rishit + Steve | Medium |
| Full ATS Integration | Connect applicant tracking system to Odoo Employees / Recruitment module | High — API integration required | Rishit | Medium |
| Subcontractor Portal Launch | External portal for vendors to submit profiles and engage on P3 deals | High — Odoo portal customization | Arian + Rishit | Medium |
| Invoice Automation | Auto-generate invoices from closed Projects / Timesheets | Medium — Odoo invoicing rules config | Rishit | High |

# 7. Risks & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep: Phase 2 & 3 expected in same 3-month window | High | High | Confirm with Stefan which items are priority. Phase 1 first, Phase 2 scoped after. |
| VPS swap usage at 83% — potential memory issues under load | Medium | High | Monitor with htop. Recommend upgrading VPS RAM before go-live if usage increases. |
| Team unfamiliar with Odoo platform — learning curve | Medium | Medium | Steve leads all config. Use Odoo documentation + AI assistance. Daily async standups. |
| DNS/SSL issues delaying platform access | Low | Medium | SSL setup pending — Steve to complete certbot setup as soon as DNS propagates. |
| Timezone gap between Steve (Asia) and Arian/Rishit | Medium | Low | Arian serves as co-lead for overlap. Async updates via Telegram group daily. |

# 8. Communication & Reporting Plan

| Activity | Frequency | Participants | Format |
| --- | --- | --- | --- |
| Daily async standup | Daily (end of day Asia time) | Steve, Arian, Rishit | Telegram group update: Done / Doing / Blocked |
| Weekly sprint review | Every Friday | Full team + Auspicious | Video call — demo progress, review blockers |
| Stakeholder update | Every 2 weeks | Auspicious → Stefan & Luan | Written summary with % completion per task |
| Phase sign-off meeting | End of Week 4 (Phase 1) / End of Month 2 | All team + Stefan + Luan | Live demo of full platform, formal sign-off |
| Ad-hoc escalation | As needed | Steve → Auspicious → Luan/Stefan | Telegram direct message, same-day response expected |

# 9. Phase 1 Acceptance Criteria

Phase 1 is considered complete and ready for sign-off when ALL of the following conditions are met:

- All 4 CRM pipelines live with correct stage definitions

- All 6 custom fields present and required on every opportunity form

- Contacts module fully configured with 10 tag types applied

- Automation rules R1-R4 tested and verified working

- Project templates created for all 3 engagement types

- Timesheets linked to Projects and Employees — test entries verified

- 3 Sales quote templates functional (Rate Card, SOW, MSC)

- CEO dashboard with 7 saved views accessible to management

- Team training session completed — all users can create and manage opportunities

- SSL (HTTPS) active on crm.intrastack.com

- At least 5 test deal records created across all 4 pipelines to verify end-to-end flow

IntraStack Solutions — Odoo CRM Platform | Project Execution Plan v1.0 | DRAFT — For Review Only

Prepared by Steve (Gia Khiem Do), Tech Lead | All timelines subject to revision after kickoff meeting